## Sheet1
Risk ID | Author | Date registered | Risk category | Description |  |  | Impact |  | Probability |  | Expected value |  | Proximity | Risk Response Categories | Risk Response | Risk Status | Risk Owner | Risk Actions
|  |  |  | Cause | Event | Effect | Inherent | Residual | Inherent | Residual | Inherent | Residual | [5 empty] | Date | Action | Actionee | Need By | Status | Age | BRAG
Note on A1: Provides a unique reference for every risk entered into the Risk Register. Best format could be CustomerID-ProjectID-CR#
Note on B1: The person who raised the risk
Note on C1: when the risk was identified.
Note on D1: The type of risk in terms of the project's chosen categories (e.g. Schedule, quality, legal etc.)
Note on E1: Describes the risk in terms of the cause, event (threat or opportunity) and effect (in words of the impact).
Note on H1: The result of a particular threat or opportunity actually occuring, or the anticipation of such a result.
Note on J1: The evaluated liklihood of a particular threat or opportunity actually happening, including a consideration of the frequency with which this may arise.
Note on L1: Cost of impact x Probability
Note on N1: This would typically state how close to the present time the risk event is anticipated to happen (e.g. Imminent, within stage, within project, beyond project). Proximity should be recorded in accordance with the project's chosen scales
Note on O1: Risk Response Categories: How the project will treat the risk in terms of the project's chosen categories, for example - For Threats: avoid, reduce, fallback, transfer, accept, share; - For opportunities: enhance, exploit, reject, share
Note on P1: Actions to resolve the risk, and these actions should be aligned to the chosen response categories. Note that more than one risk response may apply to a risk
Note on Q1: Typically described in terms of whether the risk is active or closed
Note on R1: The person responsible for managing the risk (there can be only one risk owner per risk)
Note on S1: Actions(s) needs to be implemented as described in the risk response.
Note on H2: This is the pre-response value. Recorded in accordance with the project's chosen scales.
Note on I2: This is the post-response value. Recorded in accordance with the project's chosen scales
Note on J2: This is the pre-response value. Recorded in accordance with the project's chosen scales
Note on K2: This is the pre-response value. Recorded in accordance with the project's chosen scales
Note on T2: description of the action agreed to respond the RISK
Note on U2: The person(s) who will implement the action.
Note on V2: Date by which this action should be completed
Note on W2: Status of the action, possible answers : Not Known, Not Started, InProgress, Completed.
Note on X2: Maturity of the action in days. This is the number of days it take actionee to complete the assigned action
Note on Y2: Based on the Status, Need By this action should be BRAGed.